Production Guardian — MVP 2

Early Warning · AI Detective · Smart Resolve

powered by InterSystems AI Hub

August 2026

Production Guardian Team

1. MVP 2 Overview

1.1 What MVP 2 adds

MVP 1 (Health Scan) answered a single question: is something wrong? It detects and surfaces production findings — dead jobs, hung processes, queue buildup, elevated error rates, slow processing, and system alerts — but by design it stops at surfacing. MVP 2 adds the three stages that turn detection into resolution:

- WHAT — Early Warning System. Predict that a building condition will breach before it does, rather than reporting only after the threshold is crossed.

- WHY — AI Detective. An InterSystems AI Hub agent that explains the root cause in plain language, backed by evidence gathered from the live production.

- FIX — Smart Resolve. Apply a governed, human-approved corrective action to the live production and confirm that the condition clears.

MVP 2 deliberately crosses the scope boundary that MVP 1 held. Root CLAUDE.md §2 explicitly places Smart Resolve, AI Detective, and Early Warning out of MVP 1. Because that file is shared and stable by policy, the boundary must be formally amended first — a shared-file change reviewed by all developers (see §5.1). This is the first governance task of MVP 2, not an afterthought.

This direction was anticipated. ADR 0001 (docs/decisions/0001-detection-engine-location.md) records that the detection engine runs outside IRIS for MVP 1, but notes that Smart Resolve “must act on the production and will need in-IRIS presence anyway,” and lists “Smart Resolve begins” under “Revisit when.” MVP 2 is that revisit.

1.2 The single demo scenario (deliberately just one)

For MVP 2 the team concentrates on one end-to-end scenario, so the three new stages are demonstrated deeply rather than broadly. The scenario:

- The Cloud API business operation (PatientDemographicsOperation) runs at PoolSize 1 — a single worker — and each message it sends is a POST /labdemo/patients to the patients REST dispatcher. That dispatcher (PatientDispatcher.UpsertPatient in iris/labdemo/REST/PatientDispatcher.cls) carries a hang 1, so every POST sleeps ~1 second. PoolSize 1 against a ~1s-per-message downstream therefore caps the pipeline at ~1 message per second.

- The HL7 generator increases inbound volume (“bombarding”) beyond one message per second.

- Because inflow exceeds the ~1 msg/sec ceiling, the queue in front of Cloud API builds up.

- The correct and only fix is to enlarge the Cloud API pool size (for example 1 → 4). With more workers, several of the 1-second dispatcher waits overlap concurrently, so effective throughput rises to ~4/sec and the queue drains.

This scenario is ideal for a demo for three reasons. It is real — Cloud API genuinely is PoolSize 1 in iris/labdemo/Production.cls. The cause is unambiguous — a throughput-bound single worker with inflow exceeding one message per second. And the fix is a single, safe, reversible configuration change through the exact write path that iris/labdemo/Triggers.cls already proves in production.

Setup note (Dev A). The hang 1 in PatientDispatcher.UpsertPatient is a small demo change that is not yet in the docker image — it must be landed into the image / setup so the scenario is reproducible from a clean docker compose up.

1.3 Out of scope for MVP 2

- The other five modules — Health Score, Health Summary, Performance Coach, and Ask Guardian remain later work.

- Multiple scenarios or multiple fix types — MVP 2 handles the one pool-size scenario end to end; a generalized action catalogue is a later step.

- Fully autonomous remediation — MVP 2 Smart Resolve requires human approval by default (see §4).

- Multi-production support — a single production, as in MVP 1.

2. Architecture: how MVP 2 extends what exists

MVP 1 shipped as four docker-compose services: iris (port 52773), metrics-proxy (port 3001), detection-engine (port 3002), and dashboard (port 5173). The iris service runs the Early Access “AI Hub” image irishealth-community-2026.3.0AI (build 126). InterSystems AI Hub is bundled inside that same IRIS instance — there is no separate AI Hub container. MCP tools, RBAC, the credential vault, and the audit log all live where the production data already is.

2.1 The MVP 2 data flow (WHAT → WHY → FIX)

The flow reuses the MVP 1 layers and adds three new pieces, all anchored on the single scenario:

- Detect (existing). Health Scan (the existing detection-engine) detects queue_buildup on Cloud API from the proxy metric stream. The root cause is precise: Cloud API is throughput-bound — PoolSize 1 against a ~1s-per-message downstream dispatcher (hang 1 in PatientDispatcher), so it clears ~1 msg/sec while inflow exceeds that.

- WHAT — Early Warning. The engine projects the queue-depth trend forward and estimates time-to-threshold. This is an extension inside the detection-engine, which already holds the rolling baseline and time series in memory.

- WHY — AI Detective. The finding plus a metric snapshot is sent to an AI Hub agent, which uses MCP tools to gather evidence from IRIS and calls an external LLM to produce a structured root-cause explanation and a recommended action.

- FIX — Smart Resolve. The recommended action (“increase Cloud API pool from 1 to 4”) is applied — after human approval — by invoking a governed MCP write tool that changes the pool size in the live production via Ens.Director.UpdateProduction().

- Confirm. The dashboard shows the queue draining and the finding clearing — the WHAT → WHY → FIX loop closed on one screen.

2.2 Where InterSystems AI Hub fits

AI Hub is the heart of MVP 2. Each capability maps directly onto this scenario:

- Governed AI agents. AI Detective is an AI Hub agent with a defined role: “diagnose an interoperability production issue from metrics and recommend a safe action.” The agent’s tools, model, and permissions are declared and governed centrally, not hard-coded inside a service.

- IRIS data and business logic exposed as MCP tools. The same IRIS instance exposes MCP tools the agent can call, in two classes:

  - Read tools (evidence gathering): get_host_status, get_queue_depth, get_pool_size, get_recent_errors, and get_processing_time — thin wrappers over the data the proxy and EnumerateHostStatus already surface.

  - Write tool (the action): set_pool_size(host, size) — wraps the proven Ens.Config.Production + Ens.Director.UpdateProduction() path from Triggers.cls. This tool is governed, RBAC-gated, and audited.

- Connect to external LLMs. The AI Hub agent calls an external LLM (for example Azure OpenAI or Claude) for the natural-language reasoning; the model choice is an AI Hub configuration, not code.

- IRIS RBAC. Only an authorized IRIS role may invoke the write tool set_pool_size. Read tools can be granted more broadly. The demo can therefore show that AI Detective can look without having permission to act.

- Credential management. The external LLM API key lives in the AI Hub credential store — never in frontend code, service env files, or IRIS globals.

- Audit of AI tool usage. Every MCP tool call, read and write, is recorded in the AI Hub audit log, so “the AI changed a production setting” is a reviewable, attributable event — essential for a healthcare operations tool.

Because AI Hub is bundled in the existing iris container (the EAP AI build), MVP 2 adds no new infrastructure — the agent, tools, RBAC, credentials, and audit all run where the production data already is.

2.3 AI Hub capability → MVP 2 use → where it lives

| AI Hub capability | MVP 2 use | Lives in |
| --- | --- | --- |
| Governed agent | AI Detective — diagnoses the queue-buildup finding and recommends a safe action | IRIS AI Hub instance |
| MCP read tools | get_host_status, get_queue_depth, get_pool_size, get_recent_errors, get_processing_time | IRIS AI Hub instance |
| set_pool_size (write) | The single mutating tool; wraps the Ens.Director.UpdateProduction() path from Triggers.cls | IRIS AI Hub instance |
| External LLM | Natural-language root-cause reasoning; model is a configuration, not code | AI Hub → external LLM |
| RBAC | Dedicated role gates set_pool_size; read tools granted more broadly | IRIS AI Hub instance |
| Credential vault | Holds the external LLM API key; no secrets in code or globals | IRIS AI Hub instance |
| Audit log | Records every read and write tool call as an attributable event | IRIS AI Hub instance |

2.4 New and changed contracts

The contracts/ directory is read-only: any change is a reviewed PR with a contracts/CHANGELOG.md entry, approved by all developers. MVP 2 leaves the two MVP 1 contracts unchanged and adds four new ones.

| Contract | Status | Owner | Consumers |
| --- | --- | --- | --- |
| contracts/proxy-api.md | Unchanged | Dev B (was Dev A) | detection-engine |
| contracts/healthscan-api.md | Unchanged | Dev B | dashboard |
| contracts/earlywarning-api.md | New | Dev B | Dev C |
| contracts/investigation-api.md | New | Dev B | Dev C |
| contracts/resolve-api.md | New | Dev A + Dev B | Dev C |
| contracts/mcp-tools.md | New | Dev A | Dev B |

earlywarning-api.md defines the projection schema; investigation-api.md the AI Detective request/response; resolve-api.md the Smart Resolve action and result plus the MCP write-tool boundary; and mcp-tools.md the MCP tool catalogue (names, inputs, outputs, read-vs-write, and RBAC role).

3. The demo flow (step by step)

The entire loop runs on one screen, in order:

- Healthy baseline. Cloud API shows OK, queue near zero, pool size 1.

- Start the load. The presenter increases the HL7 generator rate above one message per second (“bombard”).

- Detection. Health Scan detects queue_buildup on Cloud API. The absoluteFloor: 50 guard and the sustained-breach gate (a rule must breach 2+ consecutive samples) mean this is a real, debounced finding, not noise.

- WHAT. The Early Warning panel projects the trend: “queue rising ~N/min; at this rate it crosses threshold in ~M minutes.”

- Investigate. The presenter clicks Investigate. AI Detective (the AI Hub agent) runs: it calls the read MCP tools for evidence, calls the LLM, and returns a structured explanation.

- WHY. The investigation panel shows the root cause (“Cloud API is throughput-bound — PoolSize 1 against a ~1s-per-message downstream dispatcher, so it clears ~1 msg/sec while inflow exceeds that”), evidence bullets (Cloud API PoolSize = 1; each message ~1s from the downstream dispatcher throttle; inflow rate > 1/sec; queue slope positive), a confidence score, and the recommended action (“increase Cloud API pool 1 → 4”).

- FIX. The presenter clicks Approve & Apply on Smart Resolve. The RBAC check passes, the governed set_pool_size tool sets Cloud API pool 1 → 4 via Ens.Director.UpdateProduction(), and the call is written to the AI Hub audit log.

- Drain and clear. The queue drains on screen; the queue_buildup finding clears; pool size now shows 4.

- Audit. The presenter shows the AI Hub audit entry — who acted, what changed, and when.

4. Design decisions to make (new ADRs)

Decisions are recorded as ADRs in docs/decisions/. MVP 2 needs its own set. The following are proposed for review before development begins.

4.1 Proposed ADRs

| Decision | Recommendation | Why |
| --- | --- | --- |
| AI Detective / agent location | Run AI Detective as an AI Hub agent inside the iris container; the detection-engine orchestrates it over HTTP/MCP | AI Hub is already in that image; keeps the LLM key and audit in IRIS; ADR 0001 predicted Smart Resolve and agents moving in-IRIS |
| Where Early Warning computes | In the detection-engine (Dev B) — it already holds the time series and baseline in memory | No new component; reuses the warm baseline; keeps IRIS free of prediction code |
| MCP tool boundary (read vs write) | Separate read tools from the single write tool; only set_pool_size mutates, and only it needs the privileged RBAC role | Least privilege; lets AI Detective investigate freely while gating action |
| Smart Resolve safety | Human approval by default; a whitelist of exactly one action (set_pool_size on Cloud API, bounded range); dry-run/preview before apply; reversible | A healthcare production tool must never act unattended in a demo; bounds, approval, and reversibility make it safe on stage |
| Credential & RBAC | LLM key in the AI Hub credential vault; a dedicated IRIS role for the write tool | No secrets in code; attributable action |
| Mock-first | Keep ADR 0004: a mock AI Hub agent returns a canned structured response for this scenario, and a mock resolve simulates the pool change | Same parallelization bet that made MVP 1 work; Dev C and the demo never block on live AI |

5. Three-developer work split

The split reuses the existing ownership: Dev A owns iris/** and the AI Hub tools; Dev B owns the detection-engine and agent orchestration; Dev C owns the dashboard. All four new contracts are published on Day 1 so the three developers work in parallel against mocks (ADR 0004).

5.1 Coordination points (Day 1 contracts)

| Contract | Owner | Consumers | Agreed by |
| --- | --- | --- | --- |
| mcp-tools.md (tool catalogue, RBAC) | Dev A | Dev B | Day 1 |
| investigation-api.md (req/resp) | Dev B | Dev C | Day 1 |
| earlywarning-api.md (projection) | Dev B | Dev C | Day 1 |
| resolve-api.md (action + result) | Dev A + Dev B | Dev C | Day 1 |

In addition, the root CLAUDE.md §2 scope amendment for MVP 2 is a joint change agreed by all three developers on Day 1 — the governance gate that unblocks everything else.

5.2 Developer A — IRIS, AI Hub tools & the governed action

Dev A owns everything inside iris/**: the MCP tool definitions in AI Hub, the governed write tool, RBAC roles, the credential vault entry, audit configuration, and the HL7 generator changes needed for the demo. Dev A co-owns resolve-api.md with Dev B.

| Task | Priority | Dependency | Est. days | Deliverable |
| --- | --- | --- | --- | --- |
| Amend root CLAUDE.md §2 scope (joint PR) | Critical | — | 0.25 | Scope boundary updated |
| Define + register MCP read tools in AI Hub (get_host_status, get_queue_depth, get_pool_size, get_recent_errors, get_processing_time) | Critical | — | 1.0 | Read tools callable from AI Hub |
| Build governed write tool set_pool_size wrapping Ens.Director.UpdateProduction() (bounded range, guarded like Triggers.CheckProduction) | Critical | read tools | 1.0 | Pool change works live, RBAC-gated |
| Configure RBAC role for the write tool + LLM credential in AI Hub vault | High | write tool | 0.5 | Only authorized role can act; no key in code |
| Enable AI Hub audit for tool calls + publish mcp-tools.md and co-own resolve-api.md | High | tools | 0.5 | Every call audited; contracts published |
| Extend HL7 generator with a “bombard” rate toggle for the demo; also land the hang 1 dispatcher throttle (PatientDispatcher.cls) into the docker image / setup | Medium | — | 0.5 | Inbound rate can exceed 1/sec on cue; scenario reproducible from a clean docker compose up |

Acceptance. Read tools return real evidence; set_pool_size changes the live pool 1 → 4 and is reversible; an unauthorized role is refused; every call appears in the audit log.

5.3 Developer B — Early Warning + AI Detective orchestration

Dev B extends the detection-engine with the Early Warning projection and the AI Detective orchestration layer, publishes the two schemas Dev C mocks against, and exposes the new endpoints. The engine already holds the rolling baseline and time series, so Early Warning is an extension rather than a new component.

| Task | Priority | Dependency | Est. days | Deliverable |
| --- | --- | --- | --- | --- |
| Publish earlywarning-api.md and investigation-api.md | Critical | — | 0.5 | Schemas Dev C can mock |
| Build Early Warning projection (queue-depth slope → time-to-threshold) in the engine | Critical | — | 1.0 | Projection for Cloud API queue |
| Build AI Detective orchestration: call AI Hub agent with finding+snapshot, receive structured {rootCause, evidence[], confidence, recommendedAction} | Critical | mcp-tools.md | 1.5 | Live investigation for the scenario |
| New endpoints: GET /api/earlywarning, POST /api/investigate, POST /api/resolve (proxies the governed tool) | Critical | above | 0.75 | Endpoints serve the dashboard |
| Mock AI Hub agent (canned structured response) + mock resolve | High | schemas | 0.5 | Dev C + demo never block on live AI |

Acceptance. Early Warning projects a plausible time-to-threshold; investigation returns the structured schema; the resolve endpoint triggers the governed tool (or mock) and returns before/after values.

5.4 Developer C — MVP 2 dashboard experience (WHAT → WHY → FIX)

Dev C extends the existing dashboard, mock-first, keeping the demo/live toggle (?mode=live) and the brand tokens (navy #1B2A4A, teal #00A887). The three new panels render against mocks first, then swap to Dev B’s live endpoints.

| Task | Priority | Dependency | Est. days | Deliverable |
| --- | --- | --- | --- | --- |
| Early Warning panel (projection + countdown) against mock | High | earlywarning schema | 0.75 | Renders projection live |
| AI Detective investigation panel (root cause, evidence, confidence, recommended action) against mock | Critical | investigation schema | 1.0 | Renders structured investigation |
| Smart Resolve panel: Approve & Apply, dry-run/preview, before/after, disabled if unauthorized | Critical | resolve schema | 0.75 | Approve→apply→drain shown; RBAC state reflected |
| Wire all three to live endpoints; swap mocks | High | Dev B endpoints | 0.5 | Live WHAT→WHY→FIX loop |
| Show AI Hub audit entry for the action (read-only view) | Medium | audit available | 0.25 | Audit event visible in UI |
| Update static fallback + demo-mode scenario to include the new stages | High | panels | 0.5 | Fallback runs the full loop offline |

Acceptance. The full WHAT → WHY → FIX loop runs in the browser live; it degrades to a scripted demo-mode loop offline; the RBAC-denied state is visible.

5.5 Suggested timeline

Each developer lands roughly 3.5–4 dev-days of area work plus shared integration and rehearsal on Day 5.

| Day | Dev A | Dev B | Dev C |
| --- | --- | --- | --- |
| 1 | Scope amendment; publish mcp-tools.md; stub read tools | Publish earlywarning + investigation schemas; mock agent | Scaffold three panels against mocks |
| 2 | Read tools callable; begin write tool | Early Warning projection | Early Warning panel; start investigation panel |
| 3 | Write tool live; RBAC + credential vault | AI Detective orchestration | Investigation panel complete |
| 4 | Audit enabled; bombard toggle; resolve-api | New endpoints; mock resolve | Smart Resolve panel; audit view |
| 5 | Integration + rehearsal | Integration + rehearsal | Wire live endpoints; integration + rehearsal |

6. Risks and mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| AI Hub Early Access API/behaviour changes | High | High | All AI calls behind one adapter; mock agent first; pin the EAP image build (126); never block the demo on live AI |
| The AI writes to a live production (safety) | Medium | Critical | Human approval by default; single whitelisted action; bounded pool range; dry-run/preview; reversible; RBAC-gated; every call audited |
| External LLM unavailable / slow / rate-limited | Medium | High | Mock agent as hot standby; cache last good investigation; timeout with graceful fallback to the canned response |
| Credential exposure | Medium | High | LLM key only in the AI Hub vault; no secrets in code or globals; rotate after the demo |
| Sensitive healthcare data sent to the LLM | Medium | Critical | Send only metrics and config (pool size, queue depth, rates) — never message content or PHI; state this explicitly as a rule |
| Scope creep beyond one scenario | Medium | High | One scenario, one action, end to end; generalization is a later step; §1.3 is the boundary |
| Pool change does not drain fast enough on stage | Low | Medium | Drain rate depends on the dispatcher hang value and the chosen target pool size — rehearse both together; rehearse the load level; pre-tune the bombard rate and target pool size; demo-mode scripted drain as fallback |
| Live-demo reliability | High | High | Mock-first everywhere; static fallback runs the full loop offline; screencast backup |

7. Recommendation

7.1 Minimum viable MVP 2

The one scenario, end to end: Health Scan detects → Early Warning projects → AI Detective (an AI Hub agent plus one LLM call and the read MCP tools) explains → Smart Resolve (the governed set_pool_size, approved) fixes → the queue drains. Achievable in roughly five dev-days per developer.

7.2 First milestone (end of Day 1)

The scope boundary is amended; all four new contracts are published; MCP read tools are stubbed; the mock agent and mock resolve are up; and Dev C is building panels against mocks. This is the parallelization gate — everything after it runs in parallel.

7.3 Optional enhancements

- A second recommended action type, once the first is proven end to end.

- A Health Score delta shown before and after the fix.

- An “explain in one sentence” summary — a step toward Ask Guardian.

- Confidence-gated auto-apply for low-risk actions only.

7.4 Features to postpone

- Autonomous remediation without approval.

- Multiple scenarios or multiple action types.

- Multi-production support.

- Historical trend of interventions.

7.5 Three decisions before development begins

- AI Hub readiness. Confirm the AI Hub EAP is stable enough to build the agent against, or commit to mock-first with the adapter (recommended).

- Safety model. Confirm the human-approval-plus-single-whitelisted-action model for a live production write (recommended — never auto-act in a healthcare demo).

- LLM data boundary. Confirm exactly what data is sent to the external LLM — metrics and config only, never PHI or message content (recommended, and stated in the contract).